## Sparky AI
Primary Column | Assigned To | Status | Start Date | End Date | Duration | At Risk
Milestone 0: Kickoff |  | Complete | 2025-03-02 | 2025-03-07 | 5d
Attend meeting with Client |  | Complete | 2025-02-09 | 2025-02-12 | 3d
Milestone 1: SOC 2 Foundation |  | In Progress | 2025-02-17 | 2025-02-23 | 6d
SOC 2 research and framework review |  | In Progress | 2025-02-17
Milestone 2: Assessment & Gap Analysis |  | Not Started | 2025-02-24 | 2025-03-09 | 13d
Stakeholder Interview |  | Not Started
Milestone 3: Checklist Development |  | Not Started | 2025-03-10 | 2025-03-23 | 13d
Checklist Creation |  | Not Started
Milestone 4: Remediation Recommendations |  | Not Started | 2025-03-24 | 2025-03-30 | 6d
Reccomendation Development |  | Not Started
Milestone 5: Mid-Project Review & Refinement |  | Not Started | 2025-03-31 | 2025-04-06 | 6d
Mid-Project Review Meeting |  | Not Started
Milestone 6: Final Documentation |  | Not Started | 2025-04-07 | 2025-04-13 | 6d
Documentation |  | Not Started
Milestone 7: Presentation |  | Not Started | 2025-04-14 | 2025-04-20 | 6d
Presentation 7 & Delivery |  | Not Started
Meetings
Introduction meeting |  | Complete | 2025-02-09 | 2025-02-09 | 30m
2nd meeting with ted |  | Complete | 2025-02-12 | 2025-02-12 | 30m
Week 3 ( No Meeting Client OOTO) |  | Complete | 2025-02-17 | 2025-02-23 | N/A | TRUE
Week 4 Part 1 - Catch Up with Sparky Ai |  | Complete | 2025-02-26 | 2025-02-26 | 48m
Week 4 Part 2 - First Office Meeting at Sparky AI |  | In Progress | 2025-03-02 | 2025-03-02 | 2h