## Sparky AI
Primary Column | Assigned To | Status | Start Date | End Date | Duration | At Risk | Modified By | Modification Date
Milestone 0: Kickoff | Brian Henry | Complete | 2025-03-02 | 2025-03-07 | 5d |  | bhenry13@student.gsu.edu | 2025-03-02 09:53
Attend meeting with Client | Brian Henry | Complete | 2025-02-09 | 2025-02-12 | 3d |  | bhenry13@student.gsu.edu | 2025-02-23 17:13
Milestone 1: SOC 2 Foundation | Brian Henry | In Progress | 2025-02-17 | 2025-02-23 | 6d |  | bhenry13@student.gsu.edu | 2025-02-23 17:14
SOC 2 research and framework review | Brian Henry | In Progress | 2025-02-17 |  |  |  | bhenry13@student.gsu.edu | 2025-02-23 17:14
Milestone 2: Assessment & Gap Analysis | Brian Henry | Not Started | 2025-02-24 | 2025-03-09 | 13d |  | bhenry13@student.gsu.edu | 2025-02-23 17:13
Stakeholder Interview | Brian Henry | Not Started |  |  |  |  | bhenry13@student.gsu.edu | 2025-02-23 17:13
Milestone 3: Checklist Development | Brian Henry | Not Started | 2025-03-10 | 2025-03-23 | 13d |  | bhenry13@student.gsu.edu | 2025-02-23 17:13
Checklist Creation | Brian Henry | Not Started |  |  |  |  | bhenry13@student.gsu.edu | 2025-02-23 17:13
Milestone 4: Remediation Recommendations | Brian Henry | Not Started | 2025-03-24 | 2025-03-30 | 6d |  | bhenry13@student.gsu.edu | 2025-02-23 17:13
Reccomendation Development | Brian Henry | Not Started |  |  |  |  | bhenry13@student.gsu.edu | 2025-02-23 17:13
Milestone 5: Mid-Project Review & Refinement | Kent Cherry | Not Started | 2025-03-31 | 2025-04-06 | 6d |  | bhenry13@student.gsu.edu | 2025-02-23 17:13
Mid-Project Review Meeting | Karyss Robins | Not Started |  |  |  |  | bhenry13@student.gsu.edu | 2025-02-23 17:13
Milestone 6: Final Documentation | Karyss Robins | Not Started | 2025-04-07 | 2025-04-13 | 6d |  | bhenry13@student.gsu.edu | 2025-02-23 17:13
Documentation | Karyss Robins | Not Started |  |  |  |  | bhenry13@student.gsu.edu | 2025-02-23 17:13
Milestone 7: Presentation | Karyss Robins | Not Started | 2025-04-14 | 2025-04-20 | 6d |  | bhenry13@student.gsu.edu | 2025-02-23 17:13
Presentation 7 & Delivery | Karyss Robins | Not Started |  |  |  |  | bhenry13@student.gsu.edu | 2025-02-23 17:13
Meetings | [6 empty] | bhenry13@student.gsu.edu | 2025-02-16 15:47
Introduction meeting |  | Complete | 2025-02-09 | 2025-02-09 | 30m |  | bhenry13@student.gsu.edu | 2025-03-02 10:05
2nd meeting with ted |  | Complete | 2025-02-12 | 2025-02-12 | 30m |  | bhenry13@student.gsu.edu | 2025-03-02 10:05
Week 3 ( No Meeting Client OOTO) |  | Complete | 2025-02-17 | 2025-02-23 | N/A | TRUE | bhenry13@student.gsu.edu | 2025-03-02 10:05
Week 4 Part 1 - Catch Up with Sparky Ai |  | Complete | 2025-02-26 | 2025-02-26 | 48m |  | bhenry13@student.gsu.edu | 2025-03-02 10:05
Week 4 Part 2 - First Office Meeting at Sparky AI |  | In Progress | 2025-03-02 | 2025-03-02 | 2h |  | bhenry13@student.gsu.edu | 2025-03-02 10:05